## Project_Details
a | b
Project ID | 10
Name | The Ingenious Gentleman Don Quixote of La Mancha
Project Manager | Miguel
Project Lead | Catalna
Scope | Become a knight, find a mission and accomplish it with epic success
Objectives | Fame, get a "cantar de gesta".

## Plan
No | Phase | Task | Responsible | Status | Start | End
1.1 | Preparations | Finish reading all chivalry books | Alonso | Complete | 2020-03-01 | 2020-03-15
1.2 | Preparations | Find a horse and name it Rocinante | Alonso | Complete | 2020-03-15 | 2020-04-01
1.3 | Preparations | Find a squire | Alonso | Complete | 2020-04-01 | 2020-04-10
1.4 | Preparations | Become a knight errant | Alonso | Complete | 2020-04-11 | 2020-04-15
2.1 | Mission | Find first mission and accomplish it | Alonso | In Progress | 2020-04-15 | 2020-07-30
2.2 | Mission | Find second mission and accomplish it | Alonso | To Do | 2020-07-30 | 2020-08-06
2.3 | Mission | Find third mission and accomplish it | Alonso | To Do | 2020-08-07 | 2020-09-15
3.1 | Debrief | Come back home and write memoirs | Alonso | To Do | 2020-09-16 | 2020-11-30
3.2 | Debrief | Sign-off | Alonso | To Do | 2020-12-01 | 2020-12-01

## Updates
Date | Done | To Do
2020-03-01 | Project kicked-off | -
2020-03-01 | Sucessfully reported appearance of sea monster on all major channels. Other government have shown interested in expedition. | Find horse and squire
2020-04-15 | Found Rocinante and hired Sancho Panza as squire. Completed Knight errand ceremony without issues | Hit the road.
2020-05-15 | Attempted first mission, failed | Keep trying

## Issues
Severity | State | Issue | Impact | Action | Due | Assignee
A | Open | Sancho has a lot of attitude, keeps seeing things differently | Too many discussions | Keep training him. | 2020-06-30 | Alonso