## Project_Details
a | b
Project ID | 8
Name | Twenty Thousand Leagues Under the Sea
Project Manager | Honorine
Project Lead | Jules
Scope | This project will assemble an International expedition. The team will sail on the USS Abraham Lincoln with the sole objective of finding an destroying the sea monster, which has been destroying ships across the oceans.
Objectives | Find and destroy the sea monster.

## Plan
No | Phase | Task | Responsible | Status | Start | End
1.1 | Preparations | Report Appeareance of Sea Monster | U.S. Government | Complete | 2020-01-01 | 2020-01-15
1.2 | Preparations | Call for International Cooperation | U.S. Government | Complete | 2020-01-15 | 2020-01-31
1.3 | Preparations | Prepare Expedition Vessel | U.S. Government | Complete | 2020-02-01 | 2020-02-20
1.4 | Preparations | Assemble Team and Crew | U.S. Government | Complete | 2020-02-01 | 2020-02-20
2.1 | Mission | Sail to the High Seas | USS Lincoln's skipper | Complete | 2020-02-21 | 2020-02-21
2.2 | Mission | Find and Destroy Monster | Ned Land | In Progress | 2020-02-22 | 2020-04-05
2.3 | Mission | Come back to Port | USS Lincoln's skipper | To Do | 2020-04-06 | 2020-04-06
3.1 | Debrief | Write Report | Prof Aronnax | To Do | 2020-04-07 | 2020-04-30
3.2 | Debrief | Sign-off | U.S. Government | To Do | 2020-05-01 | 2020-05-01

## Updates
Date | Done | To Do
2020-01-01 | Project kicked-off | -
2020-01-15 | Sucessfully reported appearance of sea monster on all major channels. Other government have shown interested in expedition. | Launch call for international cooperation to conduct joint mission
2020-01-31 | International call well recevied amongst key nations. France announced they will send qualified professor. | *Start with vessel preparations in Manhattan. * Assemble team in NYC , conduct training.
2020-02-15 | - Team met in NYC, including Prof Aronnax (FR) and whaler Ned Land (CA) - USS Lincoln's prep on schedule | Prepare to sail.
2020-02-28 | Left port on time, reached Cape Horn. | Continue voyage and search for monster
2020-03-15 | Sighting reported on off coast Japan. Heading in this direction | Prepare for encounter.
2020-03-21 | Expedition captured by captain Nemo, currently on the Nautilus | Recover team and re-plan.

## Issues
Severity | State | Issue | Impact | Action | Due | Assignee
G | Closed | Time difference with Australia means announcement won't make their Friday news bulletin | Delayed response from Canberra | Give them an early memo | 2020-01-16 | Jules
A | Closed | Shortage of Tim-Tams in NYC | Won't be able to stock them on time | Order online, to pick up in Valparaiso | 2020-03-03 | Jules
R | Open | Mission suspended due to captivity aboard the Nautilus | Not able to return to port to report findings | Remain of board until released, conduct data gathering |  | Prof Aronnax
R | Open | Being kept captive by Captain Nemo | Not able to return to port to report findings | Confront Nemo, convince Aronnax to plan escape. | 2020-04-15 | Ned Land